## Sheet1
Sprint | Feature Set / Requirements ID | Topic | User Story | Task # | Task | Priorities | Assigned To | Start Date | End Date | Hours(Task Based)Estimate the testing+development-Technical Panel | Story Point(Bussiness Value/Complexity)Estimate how much we can deliver in a sprint+total efford with its task with its risk dependencies and other Factors(Pro+Scrum) | Status | Short Description of Feature Set/ Feature | Dependency of Feature Set/ Feature | Feature Owner | Feature Complexity | Business Priority | Feature Type | Remarks
1 | FS 1 / Req_1 and 2 | Admin Registration and Login | In this admin has two options.If the admin/user is new then he/she will register otherwise, login with its credentials. | Task #1 | Create the admin registeration form jsp so that new admin can enter details. Admin redirection to fill some of the basic attributes/fields as mentioned below in: (First Name, Last Name, Contact Number, , Email ID, Password ) | Critical | chandan | 20/3/19 | 23/3/19 | 6 | M | Completed | The objective of this requirement is to allow the admin to Register as a new admin and redirect to new admin registration form. | Admin being able to access the homepage & get redirected to the ‘Admin Registration’ page upon click of ‘register as admin’ link. | Scrum Master | Average | High | New Requirement
|  |  |  | Task #2 | Create Admin Entity, AdminDao, AdminController, AdminService Layer in Spring MVC to Save and Validate the Data. | Critical | chandan | 20/3/19 | 23/3/19 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task #3 | Login Validation using database , spring security and redirect to Admin Home Page | Critical | Shubham | 23/3/19 | 25/3/19 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task #4 | Integration All | Medium | Shubham | 23/3/19 | 25/3/19 | 6 | M | Completed |  | dependented on task 1 ,2 and 3 | Scrum Master | Average | High | New Requirement
1 | FS 1 / Req_3 and 4 | User Registration and Login | In this user has two options.If the user is new then he/she will register otherwise, login with its credentials. | Task #1 | Create the user registeration form jsp so that new admin can enter details. User redirection to fill some of the basic attributes/fields as mentioned below in: (First Name, Last Name, Contact Number, , Email ID, Password, Skills ) | Critical | Bikash | 23/3/19 | 25/3/19 | 6 | M | Completed | The objective of this requirement is to allow the user to Register as a new user and redirect to new user registration form. | user being able to access the homepage & get redirected to the ‘User Registration’ page upon click of ‘register as user’ link. | Scrum Master | Average | High | New Requirement
|  |  |  | Task #2 | Create User Entity, UserDao, UserController, UserService Layer in Spring MVC to Save and Validate the Data. | Critical | Bikash | 23/3/19 | 25/3/19 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task #3 | Login Validation using database , spring security and redirect to User Home Page | Critical | Bikash | 25/3/19 | 27/3/19 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task #4 | Integration All | Medium | Bikash | 25/3/19 | 27/3/19 | 6 | M | Completed |  | dependented on task 1 ,2 and 3 | Scrum Master | Average | High | New Requirement
2 | FS 2 / Req_5 | Add Project by admin | As an admin, I want to land on Add product page which will add project | Task#1 | Create a jsp page for Add project and successfully land on it after validating credentials. | High | Ashish | 29/3/19 | 2019-03-04 | 12 | M | Completed | The objective of this requirement is to allow the add project by the filling the details like(Project name,Project Description,Budget,Time and skills) |  | Scrum Master | Complex | High | New Requirement
|  |  |  | Task#2 | Create Project Entity,Project Dao,Admin Controller ,Project service Layer in Spring MVC . | Critical | Ashish | 29/3/19 | 2019-03-04 | 12 | L | Completed |  |  | Scrum Master | Complex | High | New Requirement
|  |  |  | Task#6 | Integrate the code and verify its working. | Critical | Ashish | 29/3/19 | 2019-03-04 | 12 | M | Completed |  |  | Scrum Master | Complex | High | New Requirement
| FS 3/Req_6 | View Project By admin | As an admin,I want to view existing project and respond to proposal request | Task#1 | Create a registeration JSP page to existing project and to accept the proposal from user | Critical | Ashish | 2019-03-04 | 2019-06-04 | 12 | M | Completed | The objective of this requirement is to allow the admin to view project and to accept or reject user propsal |  | Scrum Master | Complex | High | New Requirement
|  |  |  | Task#2 | Create Project Entity,Project Dao,Admin Controller ,Project service Layer in Spring MVC . | Critical | Ashish | 2019-03-04 | 2019-06-04 | 12 | L | Completed |  |  | Scrum Master | Complex | High | New Requirement
|  |  |  | Task#3 | Integrate the code and verify its working. | Critical | Shubham | 2019-03-04 | 2019-06-04 | 12 | M | Completed |  |  | Scrum Master | Complex | High | New Requirement
3 | FS 4 / Req_7 | User Home | As an user, I want to land on User Home page which will display all the project from the database | Task#1 | Create a jsp page for User Home and successfully land on it after validating credentials. |  | Sagar | 2019-06-04 | 2019-09-04 | 6 | M | Completed | The objective of this requirement is to allow the user to view existing project and send proposal request |  | Scrum Master | Complex | High | New Requirement
|  |  |  | Task#2 | Edit Project Entity,Project Dao,User Controller ,Project service Layer in Spring MVC . | Critical | Sagar | 2019-06-04 | 2019-09-04 | 12 | L | Completed |  |  | Scrum Master | Complex | High | New Requirement
|  |  |  | Task#3 | Integrate the code and verify its working. | Critical | sagar | 2019-06-04 | 2019-09-04 | 12 | M | Completed |  |  | Scrum Master | Complex | High | New Requirement
|  | Propsal request to admin | As an user, I want to send project prosal to admin | Task#4 | By clicking on the 'send Proposal' one should be able to send proposal to admin |  | Sagar | 2019-06-04 | 2019-09-04 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#5 | Create a jsp page with proposal options |  | Sagar | 2019-09-04 | 2019-10-04 | 6 | M | Completed |  | dependented on task 1 ,2 and 3 | Scrum Master | Average | High | New Requirement
| FS 5/ Req_8 | Update user Skills | As an user, I want to send project prosal to admin | Task#1 | Create a jsp page for User skill update |  | Bikash | 2019-10-04 | 2019-11-04 | 6 | M | Completed | The objective of this requirement is to allow the user to update his skills. |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#2 | Create a User entity, updateDAO, update Service and controller |  | Chandan | 2019-10-04 | 2019-11-04 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#3 | Integrate the code and verify its working. |  | Shubham | 2019-11-04 | 2019-12-04 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  | As a admin I want to upate my phone no and password | Task#8 | Create a jsp page for admin update |  | Bikash | 2019-12-04 | 13/4/2019 | 6 | M | Completed | The objective of this requirement is to allow the user to update his password and phone no. |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#2 | Create a User entity, updateDAO, update Service and controller |  | Sagar | 2019-12-04 | 13/4/2020 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#3 | Integrate the code and verify its working. |  | Shubham | 2019-12-04 | 13/4/2021 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement